## Week 2
Time Sheet ¦ Name: Noah Miera |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Team/Scrum Leader |  |  |  |  | Time Sheet ¦ Name: Keith Gross |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Programer
[6 empty] | Week 2 | [14 empty] | Week 2
[5 empty] | 1/30-2022 - 2/5/2022 | [14 empty] | 1/30-2022 - 2/5/2022
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-01-30 |  | 2022-01-31 |  | 2022-02-01 |  | 2022-02-02 |  | 2022-02-03 |  | 2022-02-04 |  | 2022-02-05 |  |  | 2022-01-30 |  | 2022-01-31 |  | 2022-02-01 |  | 2022-02-02 |  | 2022-02-03 |  | 2022-02-04 |  | 2022-02-05
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL |  | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
2.1 | [6 empty] | 1 | 0.5 | [6 empty] | 2.1 | [6 empty] | 1 | 1
3 | [8 empty] | 1.2 | 1.2 |  |  |  |  | 3 | [8 empty] | 1.2 | 1.2
[11 empty] | TOTAL | PLANNED: | 2.2 | [12 empty] | TOTAL | PLANNED: | 2.2
Signature: | [11 empty] | ACTUAL: | 1.7 |  | Signature: | [11 empty] | ACTUAL: | 2.2
Time Sheet ¦ Name: Juan Gonzalez |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Project Manager |  |  |  |  | Time Sheet ¦ Name: Miguel Morales |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Programer
[6 empty] | Week 2 | [14 empty] | Week 2
[5 empty] | 1/30-2022 - 2/5/2022 | [14 empty] | 1/30-2022 - 2/5/2022
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-01-30 |  | 2022-01-31 |  | 2022-02-01 |  | 2022-02-02 |  | 2022-02-03 |  | 2022-02-04 |  | 2022-02-05 |  |  | 2022-01-30 |  | 2022-01-31 |  | 2022-02-01 |  | 2022-02-02 |  | 2022-02-03 |  | 2022-02-04 |  | 2022-02-05
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL |  | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
2.1 | [6 empty] | 1 | 1.5 | [6 empty] | 2.1 | [6 empty] | 1 | 1
3 | [8 empty] | 1.2 | 1.2 |  |  |  |  | 3 | [8 empty] | 1.2 | 1.2
[11 empty] | TOTAL | PLANNED: | 2.2 | [12 empty] | TOTAL | PLANNED: | 2.2
Signature: | [11 empty] | ACTUAL: | 2.7 |  | Signature: | [11 empty] | ACTUAL: | 2.2
Time Sheet ¦ Name: Jordan Fisher |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Documentation/Training
[6 empty] | Week 2 | [11 empty] | 10.5
1/30-2022 - 2/5/2022
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-01-30 |  | 2022-01-31 |  | 2022-02-01 |  | 2022-02-02 |  | 2022-02-03 |  | 2022-02-04 |  | 2022-02-05
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
2.1 | [6 empty] | 1 | 0.5
3 | [8 empty] | 1.2 | 1.2
[11 empty] | TOTAL | PLANNED: | 2.2
Signature: | [11 empty] | ACTUAL: | 1.7

## Week 3
Time Sheet ¦ Name: Noah Miera |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Team/Scrum Leader |  |  |  |  | Time Sheet ¦ Name: Keith Gross |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Programer
[6 empty] | Week 3 | [14 empty] | Week 3
[5 empty] | 2/6-2022 - 2/12/2022 | [14 empty] | 2/6-2022 - 2/12/2022
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-02-06 |  | 2022-02-07 |  | 2022-02-08 |  | 2022-02-09 |  | 2022-02-10 |  | 2022-02-11 |  | 2022-02-12 |  |  | 2022-02-06 |  | 2022-02-07 |  | 2022-02-08 |  | 2022-02-09 |  | 2022-02-10 |  | 2022-02-11 |  | 2022-02-12
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL |  | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
4.1.1 | 0.5 | 1 | [12 empty] | 4.1.1 | 0.5 | 1
4.1.2 |  |  | 0.25 | 0.5 | [10 empty] | 4.1.2 |  |  | 0.25 | 0.25
4.2.1 | [6 empty] | 0.25 | 0.25 | [6 empty] | 4.2.1 | [6 empty] | 0.25 | 0.25
4.2.2 | [8 empty] | 1 | 1 |  |  |  |  | 4.2.2 | [8 empty] | 1 | 1
4.2.3 | [10 empty] | 0.25 | 0.25 |  |  | 4.2.3 | [10 empty] | 0.25 | 0.25
4.4.1-4.3.1-4.3.2-4.3.3 | [12 empty] | 2 | 4 | 4.51 | [12 empty] | 1.5 | 3
[11 empty] | TOTAL | PLANNED: | 4.25 | [12 empty] | TOTAL | PLANNED: | 3.75
Signature: | [11 empty] | ACTUAL: | 7 |  | Signature: | [11 empty] | ACTUAL: | 5.75
Time Sheet ¦ Name: Juan Gonzalez |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Project Manager |  |  |  |  | Time Sheet ¦ Name: Miguel Morales |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Programer
[6 empty] | Week 3 | [14 empty] | Week 3
[5 empty] | 2/6-2022 - 2/12/2022 | [14 empty] | 2/6-2022 - 2/12/2022
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-02-06 |  | 2022-02-07 |  | 2022-02-08 |  | 2022-02-09 |  | 2022-02-10 |  | 2022-02-11 |  | 2022-02-12 |  |  | 2022-02-06 |  | 2022-02-07 |  | 2022-02-08 |  | 2022-02-09 |  | 2022-02-10 |  | 2022-02-11 |  | 2022-02-12
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL |  | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
4.1.1 | 0.5 | 1 | [12 empty] | 4.1.1 | 0.5 | 1
4.1.2 |  |  | 0.25 | 0.5 | [10 empty] | 4.1.2 |  |  | 0.25 | 0.25
4.2.1 | [6 empty] | 0.25 | 0.25 | [6 empty] | 4.2.1 | [6 empty] | 0.25 | 0
4.2.2 | [8 empty] | 1 | 1 |  |  |  |  | 4.2.2 | [8 empty] | 1 | 1
4.2.3 | [10 empty] | 0.25 | 0.25 |  |  | 4.2.3 | [10 empty] | 0.25 | 0.25
4.4.1-4.3.1-4.3.2-4.3.3 | [12 empty] | 2 | 4 | 4.51 | [12 empty] | 1.5 | 1.5
[11 empty] | TOTAL | PLANNED: | 4.25 | [12 empty] | TOTAL | PLANNED: | 3.75
Signature: | [11 empty] | ACTUAL: | 7 |  | Signature: | [11 empty] | ACTUAL: | 4
Time Sheet ¦ Name: Jordan Fisher |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Documentation/Training
Week 3
2/6-2022 - 2/12/2022
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-02-06 |  | 2022-02-07 |  | 2022-02-08 |  | 2022-02-09 |  | 2022-02-10 |  | 2022-02-11 |  | 2022-02-12
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
4.1.1 | 0.5 | 1
4.1.2 |  |  | 0.25 | 0.5
4.2.1 | [6 empty] | 0.25 | 0.25
4.2.2 | [8 empty] | 1 | 1
4.2.3 | [10 empty] | 0.25 | 0.25
4.4.1-4.3.1-4.3.2-4.3.3 | [12 empty] | 2 | 4
[11 empty] | TOTAL | PLANNED: | 4.25
Signature: | [11 empty] | ACTUAL: | 7

## Week 4
Time Sheet ¦ Name: Noah Miera |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Team/Scrum Leader |  |  |  |  | Time Sheet ¦ Name: Keith Gross |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Programer
[6 empty] | Week 4 | [14 empty] | Week 4
[5 empty] | 2022-02-13 | - | 2022-02-19 | [12 empty] | 2022-02-13 | - | 2022-02-19
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-02-13 |  | 2022-02-14 |  | 2022-02-15 |  | 2022-02-16 |  | 2022-02-17 |  | 2022-02-18 |  | 2022-02-19 |  |  | 2022-02-13 |  | 2022-02-14 |  | 2022-02-15 |  | 2022-02-16 |  | 2022-02-17 |  | 2022-02-18 |  | 2022-02-19
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL |  | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
4.5.2 | 0.5 | 0.5 | [12 empty] | 4.5.2 | 0.5 | 0.5
4.5.3 |  |  | 0.25 | 0.25 | [10 empty] | 4.5.3 |  |  | 0.25 | 0.25
4.4.1-4.3.1-4.3.2-4.3.3 | 2 | 8 | [12 empty] | 4.51 | 1.5 | 3
[11 empty] | TOTAL | PLANNED: | 2.75 | [12 empty] | TOTAL | PLANNED: | 2.25
Signature: | [11 empty] | ACTUAL: | 8.75 |  | Signature: | [11 empty] | ACTUAL: | 3.75
Time Sheet ¦ Name: Juan Gonzalez |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Project Manager |  |  |  |  | Time Sheet ¦ Name: Miguel Morales |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Programer
[6 empty] | Week 4 | [14 empty] | Week 4
[5 empty] | 2022-02-13 | - | 2022-02-19 | [12 empty] | 2022-02-13 | - | 2022-02-19
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-02-13 |  | 2022-02-14 |  | 2022-02-15 |  | 2022-02-16 |  | 2022-02-17 |  | 2022-02-18 |  | 2022-02-19 |  |  | 2022-02-13 |  | 2022-02-14 |  | 2022-02-15 |  | 2022-02-16 |  | 2022-02-17 |  | 2022-02-18 |  | 2022-02-19
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL |  | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
4.5.2 | 0.5 | 0.5 | [12 empty] | 4.5.2 | 0.5 | 0.5
4.5.3 |  |  | 0.25 | 0.25 | [10 empty] | 4.5.3 |  |  | 0.25 | 0.25
4.4.1-4.3.1-4.3.2-4.3.3 | 2 | 6.5 | [12 empty] | 4.51 | 1.5 | 2
[11 empty] | TOTAL | PLANNED: | 2.75 | [12 empty] | TOTAL | PLANNED: | 2.25
Signature: | [11 empty] | ACTUAL: | 7.25 |  | Signature: | [11 empty] | ACTUAL: | 2.75
Time Sheet ¦ Name: Jordan Fisher |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Documentation/Training
Week 4
[5 empty] | 2022-02-13 | - | 2022-02-19
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-02-13 |  | 2022-02-14 |  | 2022-02-15 |  | 2022-02-16 |  | 2022-02-17 |  | 2022-02-18 |  | 2022-02-19
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
4.5.2 | 0.5 | 0.5
4.5.3 |  |  | 0.25 | 0.25
4.4.1-4.3.1-4.3.2-4.3.3 | 2 | 8
[11 empty] | TOTAL | PLANNED: | 2.75
Signature: | [11 empty] | ACTUAL: | 8.75