## Sheet1
ID | Task Name | Assigned | Duration | Start | Finish | Estimated time (hours) |  |  |  | Upcoming meetings
1 | Phase 0: Inititial project start up -Total time: |  | 3 Days | 2022-01-28 | 2022-01-30 | Total: | 10 |  |  | week | date | Type
1.1 | Team Drive Hub and Documnetation created | All | 1 Day | 2022-01-28 | 2022-01-28 | 5 |  |  |  | 4 | 2022-02-14 | Scrum
1.2 | Crafting report 0 / Establishing team roles / Determining meeting times | All | 3 Days | 2022-01-28 | 2022-01-30 | 5 |  |  |  |  | 2022-02-15 | Scrum
2 | Research & Requirement Analysis |  | 3 Days | 2022-02-01 | 2022-02-03 | Total: | 5 |  |  |  | 2022-02-16 | Scrum
2.1 | TACO documentation and code | All | 3 Days | 2022-02-01 | 2022-02-03 | 5 |  |  |  |  | 2022-02-18 | Scrum
3 | 1st Team Meeting | All | 1 Day | 2022-02-03 | 2022-02-03 | Total: | 6 |  |  | 5 | 2022-02-21 | Scrum
[6 empty] | Total: | 21 | (Total for Phase 0) |  |  | 2022-02-22 | Scrum
4 | Phase 1: JAD #1 |  | 5 Days | 2022-02-03 | 2022-02-07 | [5 empty] | 2022-02-23 | Scrum
4.1 | Prepare for JAD 1 | All | 5 Days | 2022-02-03 | 2022-02-07 | Total: | 2.5 |  |  |  | 2022-02-25 | Scrum
4.1.1 | Sprint Meeting | All | 1 Day | 2022-02-06 | 2022-02-06 | 1.25 |  |  |  |  | 2022-02-26 | Sprint | Saturday
4.1.2 | Scrum Meeting | All | 1 Day | 2022-02-07 | 2022-02-07 | 1.25 |  |  |  | 6 | 2022-02-27 | Scrum
4.2 | Machine Learning Setup/Configuration |  | 3 Days | 2022-02-09 | 2022-02-11 | Total: | 6.25 |  |  |  | 2022-02-28 | Scrum
4.2.1 | Scrum Meeting | All | 1 Day | 2022-02-09 | 2022-02-09 | 1.25 |  |  |  |  | 2022-03-01 | Scrum
4.2.2 | Meeting with Jared | All | 1 Day | 2022-02-10 | 2022-02-10 | 5 |  |  | End of Phase 2 |  | 2022-03-02 | Sprint | Wednesday
4.2.3 | Scrum Meeting | All | 1 Day | 2022-02-11 | 2022-02-11 | 1.25 |  |  |  | 7 | 2022-03-06 | Sprint | Sunday
4.3 | Project Management |  | 3 Days | 2022-02-11 | 2022-02-13 | Total: | 6.75 |  |  |  | 2022-03-07 | Scrum
4.3.1 | Gantt Chart Development | Juan / Noah | 3 Days | 2022-02-11 | 2022-02-13 | 4 |  |  |  |  | 2022-03-08 | Scrum
4.3.2 | Timesheets | Juan / Jordan | 3 Days | 2022-02-11 | 2022-02-13 | 2 |  |  |  |  | 2022-03-09 | Scrum
4.3.3 | Costs Estimates | Noah / Juan / Jordan | 3 Days | 2022-02-11 | 2022-02-13 | 0.75 |  |  |  |  | 2022-03-12 | Scrum
4.4 | Report 1 |  | 11 Days | 2022-02-11 | 2022-02-21 | Total: | 15 |  |  | 8 | 2022-03-13 | Sprint | Sunday
4.4.1 | Report 1 (draft) | Noah / Juan / Jordan | 4 Days | 2022-02-11 | 2022-02-14 | 12 |  |  |  |  | 2022-03-14 | Scrum
4.4.2 | Report 1 (revisions) | Noah / Juan / Jordan | 11 Days | 2022-02-11 | 2022-02-21 | 3 |  |  |  |  | 2022-03-15 | Scrum
4.5 | Machine Learning Development |  | 6 Days | 2022-02-11 | 2022-02-16 | Total: | 21.25 |  |  |  | 2022-03-16 | Scrum
4.5.1 | Adapt TACO - Initial ML Algorithim Development | Miguel / Keith | 6 Days | 2022-02-11 | 2022-02-16 | 6 |  |  |  |  | 2022-03-18 | Scrum
4.5.2 | Sprint Meeting | All | 1 Day | 2022-02-13 | 2022-02-13 | 2.5 |  |  |  | 9 | 2022-03-21 | Sprint | Monday
4.5.3 | Scrum Meeting | All | 1 Day | 2022-02-14 | 2022-02-14 | 1.25 |  |  |  |  | 2022-03-22 | Scrum
4.5.4 | Adapt TACO - Initial ML Algorithim Development | All | 2 Days | 2022-02-15 | 2022-02-16 | 9 |  |  |  |  | 2022-03-23 | Scrum
4.5.5 | Scrum Meeting | All | 1 Day | 2022-02-15 | 2022-02-15 | 1.25 |  |  |  |  | 2022-03-25 | Scrum
4.5.6 | Scrum Meeting | All | 1 Day | 2022-02-16 | 2022-02-16 | 1.25 |  |  |  |  | 2022-03-26 | Scrum
[6 empty] | Total: | 51.75 | (Total for Phase 1) |  | 10 | 2022-03-27 | Sprint | Sunday
5 | Phase 2: JAD #2 | [9 empty] | 2022-03-28 | Scrum
5.1 | Prepare for JAD 2 |  | 4 Days | 2022-02-17 | 2022-02-21 | Total: | 2.5 |  |  |  | 2022-03-30 | Scrum
5.1.1 | Scrum Meeting | All | 1 Day | 2022-02-18 | 2022-02-18 | 1.25 |  |  |  |  | 2022-03-31 | Scrum
5.1.2 | Scrum Meeting | All | 1 Day | 2022-02-21 | 2022-02-21 | 1.25 |  |  |  |  | 2022-04-02 | Scrum
5.2 | Machine Learning Development |  | 6 Days | 2022-02-17 | 2022-02-23 | Total: | 32 |  |  | 11 | 2022-04-03 | Sprint | Sunday
5.2.1 | Meeting with Jared | All | 1 Day | 2022-02-17 | 2022-02-17 | 6 |  |  |  |  | 2022-04-04 | Scrum
5.2.2 | Adapt TACO - ML Algorithim Development | Miguel / Keith | 6 Days | 2022-02-18 | 2022-02-23 | 6 |  |  |  |  | 2022-04-05 | Scrum
5.2.3 | Scrum Meeting | All | 1 Day | 2022-02-18 | 2022-02-18 | 1.25 |  |  |  |  | 2022-04-06 | Scrum
5.2.4 | Scrum Meeting | All | 1 Day | 2022-02-21 | 2022-02-21 | 1.25 |  |  |  |  | 2022-04-09 | Scrum
5.2.5 | Scrum Meeting | All | 1 Day | 2022-02-22 | 2022-02-22 | 1.25 |  |  |  | 12 | 2022-04-10 | Sprint | Sunday
5.2.6 | Adapt TACO - ML Algorithim Development | All | 1 Day | 2022-02-23 | 2022-02-23 | 9 |  |  |  |  | 2022-04-11 | Scrum
5.2.7 | Scrum Meeting | All | 1 Day | 2022-02-23 | 2022-02-23 | 1.25 |  |  |  |  | 2022-04-12 | Scrum
5.2.8 | Meeting with Jared | All | 1 Day | 2022-02-24 | 2022-02-24 | 6 |  |  |  |  | 2022-04-13 | Scrum
5.3 | Project Management |  |  | 2022-02-25 | 2022-02-27 | Total: | 2.5 |  |  |  | 2022-04-16 | Scrum |  |  |  |  | 0 | 241.5 | 483
5.3.1 | Gantt Chart Development | Juan | 3 Days | 2022-02-25 | 2022-02-27 | 0.5 |  |  |  | 13 | 2022-04-17 | Sprint | Sunday
5.3.2 | Timesheets | Juan | 3 Days | 2022-02-25 | 2022-02-27 | 0.5 |  |  |  |  | 2022-04-18 | Scrum
5.3.3 | Costs Estimates | Noah / Juan / Jordan | 3 Days | 2022-02-25 | 2022-02-27 | 1.5 |  |  |  |  | 2022-04-19 | Scrum
5.4 | Report 2 |  |  | 2022-02-25 | 2022-03-08 | Total: | 12 |  |  |  | 2022-04-20 | Scrum
5.4.1 | Report 2 (draft) | Noah / Juan / Jordan | 4 Days | 2022-02-25 | 2022-02-28 | 9 |  |  |  |  | 2022-04-23 | Scrum
5.4.2 | Report 2 (revisions) | Noah / Juan / Jordan | 9 Days | 2022-02-25 | 2022-03-08 | 3 |  |  |  | 14 | 2022-04-24 | Sprint | Sunday |  |  | Due dates
5.5 | Machine Learning Development |  |  | 2022-02-25 | 2022-03-02 | Total: | 23.75 |  |  |  | 2022-04-25 | Scrum |  |  |  | JAD/Protoypes
5.5.1 | Process Images - ML Algorithim Development | Miguel / Keith | 6 Days | 2022-02-25 | 2022-03-02 | 6 |  |  |  |  | 2022-04-26 | Scrum |  |  |  | Reports
5.5.2 | Scrum Meeting | All | 1 Day | 2022-02-25 | 2022-02-25 | 1.25 |  |  |  |  | 2022-04-27 | Scrum |  |  |  | Regular Meetings
5.5.3 | Sprint Meeting | All | 1 Day | 2022-02-26 | 2022-02-26 | 2.5 |  |  |  |  | 2022-04-30 | Scrum |  |  |  | Jared Meetings
5.5.4 | Scrum Meeting | All | 1 Day | 2022-02-27 | 2022-02-27 | 1.25 |  |  |  | 15 | 2022-05-01 | Sprint | Sunday
5.5.5 | Scrum Meeting | All | 1 Day | 2022-02-28 | 2022-02-28 | 1.25 |  |  |  |  | 2022-05-02 | Scrum
5.5.6 | Process Images - ML Algorithim Development | All | 2 Days | 2022-03-01 | 2022-03-02 | 9 |  |  |  |  | 2022-05-03 | Scrum
5.5.7 | Scrum Meeting | All | 1 Day | 2022-03-01 | 2022-03-01 | 1.25 |  |  |  |  | 2022-05-04 | Scrum
5.5.8 | Sprint Meeting | All | 1 Day | 2022-03-02 | 2022-03-02 | 1.25 |  |  |  |  | 2022-05-07 | Scrum |  |  | Phases | Actual | Estimate
[10 empty] | 16 | 2022-05-08 | Sprint | Sunday
6 | Phase 3: Prototype #1 |  |  |  |  | Total: | 72.75 | (Total for Phase 2) | [6 empty] | 1 | 1426 | 1190.25
6.1 | Prepare for Prototype 1 |  |  | 2022-03-02 | 2022-03-28 | Total: | 30 | [7 empty] | 2 | 0 | 1673.25
6.1.1 | Sprint Meeting | All | 1 Day | 2022-03-02 | 2022-03-02 | 2.5 | [8 empty] | 3 | 0 | 2116
6.1.2 | Scrum Meeting | All | 1 Day | 2022-03-05 | 2022-03-05 | 1.25 |  |  |  |  | 2022-05-09 | Scrum |  |  | 4 | 0 | 1690.5
6.1.3 | Sprint Meeting | All | 1 Day | 2022-03-06 | 2022-03-06 | 2.5 |  |  |  |  | 2022-05-10 | Scrum |  |  | 5 | 0 | 1627.25
6.1.4 | Scrum Meeting | All | 1 Day | 2022-03-07 | 2022-03-07 | 1.25 |  |  |  |  | 2022-05-11 | Scrum |  |  | Total | 1426 | 8780.25
6.1.5 | Scrum Meeting | All | 1 Day | 2022-03-08 | 2022-03-08 | 1.25 |  |  |  |  | 2022-05-13 | Scrum
6.1.6 | Scrum Meeting | All | 1 Day | 2022-03-09 | 2022-03-09 | 1.25
6.1.7 | Scrum Meeting | All | 1 Day | 2022-03-12 | 2022-03-12 | 1.25
6.1.8 | Sprint Meeting | All | 1 Day | 2022-03-13 | 2022-03-13 | 2.5
6.1.9 | Scrum Meeting | All | 1 Day | 2022-03-14 | 2022-03-14 | 1.25
6.1.10 | Scrum Meeting | All | 1 Day | 2022-03-15 | 2022-03-15 | 1.25
6.1.11 | Scrum Meeting | All | 1 Day | 2022-03-16 | 2022-03-16 | 1.25 |  |  |  | Total Labor Cost Estimate: | [5 empty] | Extra Costs:
6.1.12 | Scrum Meeting | All | 1 Day | 2022-03-18 | 2022-03-18 | 1.25 |  |  |  | Phase 0 | [5 empty] | Item: | Est. Cost
6.1.13 | Sprint Meeting | All | 1 Day | 2022-03-21 | 2022-03-21 | 2.5 |  |  |  | Total Hours X |  | Hourly Rate = |  | Total Labor Cost |  | Server | 120
6.1.14 | Scrum Meeting | All | 1 Day | 2022-03-22 | 2022-03-22 | 1.25 |  |  |  | 21 | X | 23 | = | 483
6.1.15 | Scrum Meeting | All | 1 Day | 2022-03-23 | 2022-03-23 | 1.25 |  |  |  | Phase 1
6.1.16 | Scrum Meeting | All | 1 Day | 2022-03-25 | 2022-03-25 | 1.25 |  |  |  | Total Hours X |  | Hourly Rate = |  | Total Labor Cost
6.1.17 | Scrum Meeting | All | 1 Day | 2022-03-26 | 2022-03-26 | 1.25 |  |  |  | 51.75 | X | 23 | = | 1190.25
6.1.18 | Sprint Meeting | All | 1 Day | 2022-03-27 | 2022-03-27 | 2.5 |  |  |  | Phase 2
6.1.19 | Scrum Meeting | All | 1 Day | 2022-03-28 | 2022-03-28 | 1.25 |  |  |  | Total Hours X |  | Hourly Rate = |  | Total Labor Cost
6.2 | Machine Learning Development |  |  | 2022-03-03 | 2022-03-16 | Total: | 21.5 |  |  | 72.75 | X | 23 | = | 1673.25
6.2.1 | Meeting with Jared | All | 1 Day | 2022-03-03 | 2022-03-03 | 5 |  |  |  | Phase 3
6.2.2 | Process Images - ML Algorithim Development | All | 1 Day | 2022-03-04 | 2022-03-09 | 9 |  |  |  | Total Hours X |  | Hourly Rate = |  | Total Labor Cost
6.2.3 | Scrum Meeting | All | 1 Day | 2022-03-05 | 2022-03-05 | Listed above |  |  |  | 92 | X | 23 | = | 2116
6.2.4 | Sprint Meeting | All | 1 Day | 2022-03-06 | 2022-03-06 | Listed above |  |  |  | Phase 4 |  |  |  | Total Labor Cost
6.2.5 | Scrum Meeting | All | 1 Day | 2022-03-07 | 2022-03-07 | Listed above |  |  |  | Total Hours X |  | Hourly Rate = |  | Total Cost
6.2.6 | Scrum Meeting | All | 1 Day | 2022-03-08 | 2022-03-08 | Listed above |  |  |  | 73.5 | X | 23 | = | 1690.5
6.2.7 | Scrum Meeting | All | 1 Day | 2022-03-09 | 2022-03-09 | Listed above |  |  |  | Phase 5
6.2.8 | Meeting with Jared | All | 1 Day | 2022-03-10 | 2022-03-10 | 5 |  |  |  | Total Hours X |  | Hourly Rate = |  | Total Labor Cost |  | Total: | 120
6.2.9 | Process Images - ML Algorithim Development | All | 6 Days | 2022-03-11 | 2022-03-16 | 2.5 |  |  |  | 70.75 | X | 23 | = | 1627.25
6.2.10 | Scrum Meeting | All | 1 Day | 2022-03-12 | 2022-03-12 | Listed above | [5 empty] | Sum of labor costs: |  | Total Extra costs: |  | Total Estimate:
6.2.11 | Sprint Meeting | All | 1 Day | 2022-03-13 | 2022-03-13 | Listed above |  |  |  | Project total = |  | 8780.25 | + | 120 | = | 8900.25
6.2.12 | Scrum Meeting | All | 1 Day | 2022-03-14 | 2022-03-14 | Listed above
6.2.13 | Scrum Meeting | All | 1 Day | 2022-03-15 | 2022-03-15 | Listed above
6.2.14 | Scrum Meeting | All | 1 Day | 2022-03-16 | 2022-03-16 | Listed above
6.3 | Project Management |  |  |  |  | Total: | 15.5
6.3.1 | Gantt Chart Development | Juan | 4 Days | 2022-03-17 | 2022-03-20 | 1.5
6.3.2 | Timesheets | Juan | 4 Days | 2022-03-17 | 2022-03-20 | 0.5
6.3.3 | Costs Estimates | Noah / Juan / Jordan | 4 Days | 2022-03-17 | 2022-03-20 | 1.5
6.4 | Report 3
6.4.1 | Report 3 (draft) | Noah / Juan / Jordan | 19 Days | 2022-03-17 | 2022-04-04 | 9
6.4.2 | Report 3 (revisions) | Noah / Juan / Jordan | 26 Days | 2022-03-17 | 2022-04-11 | 3
6.5 | Machine Learning Development |  |  |  |  | Total: | 25
6.5.1 | Meeting with Jared | All | 1 Day | 2022-03-17 | 2022-03-17 | 5
6.5.2 | Schedule Hook - Web App Integration | Miguel / Keith | 6 Days | 2022-03-18 | 2022-03-23 | 6
6.5.3 | Scrum Meeting | All | 1 Day | 2022-03-18 | 2022-03-18 | Listed above
6.5.4 | Sprint Meeting | All | 1 Day | 2022-03-21 | 2022-03-21 | Listed above
6.5.5 | Scrum Meeting | All | 1 Day | 2022-03-22 | 2022-03-22 | Listed above
6.5.6 | Scrum Meeting | All | 1 Day | 2022-03-23 | 2022-03-23 | Listed above
6.5.7 | Meeting with Jared | All | 1 Day | 2022-03-24 | 2022-03-24 | 5
6.5.8 | Prepare Image Data - Process Results | All | 4 Days | 2022-03-25 | 2022-03-28 | 9
6.5.9 | Scrum Meeting | All | 1 Day | 2022-03-25 | 2022-03-25 | Listed above
6.5.10 | Scrum Meeting | All | 1 Day | 2022-03-26 | 2022-03-26 | Listed above
6.5.11 | Sprint Meeting | All | 1 Day | 2022-03-27 | 2022-03-27 | Listed above
6.5.12 | Scrum Meeting | All | 1 Day | 2022-03-28 | 2022-03-28 | Listed above
7 | Phase 4: Prototype #2 |  |  |  |  | Total: | 92 | (Total for Phase 3)
7.1 | Prepare for Prototype 2 |  |  | 2022-03-30 | 2022-04-21 | Total: | 25
7.1.1 | Scrum Meeting | All | 1 Day | 2022-03-30 | 2022-03-30 | 1.25
7.1.2 | Scrum Meeting | All | 1 Day | 2022-03-31 | 2022-03-31 | 1.25
7.1.3 | Scrum Meeting | All | 1 Day | 2022-04-02 | 2022-04-02 | 1.25
7.1.4 | Sprint Meeting | All | 1 Day | 2022-04-03 | 2022-04-03 | 2.5
7.1.5 | Scrum Meeting | All | 1 Day | 2022-04-04 | 2022-04-04 | 1.25
7.1.6 | Scrum Meeting | All | 1 Day | 2022-04-05 | 2022-04-05 | 1.25
7.1.7 | Scrum Meeting | All | 1 Day | 2022-04-06 | 2022-04-06 | 1.25
7.1.8 | Scrum Meeting | All | 1 Day | 2022-04-09 | 2022-04-09 | 1.25
7.1.9 | Sprint Meeting | All | 1 Day | 2022-04-10 | 2022-04-10 | 2.5
7.1.10 | Scrum Meeting | All | 1 Day | 2022-04-11 | 2022-04-11 | 1.25
7.1.11 | Scrum Meeting | All | 1 Day | 2022-04-12 | 2022-04-12 | 1.25
7.1.12 | Scrum Meeting | All | 1 Day | 2022-04-13 | 2022-04-13 | 1.25
7.1.13 | Scrum Meeting | All | 1 Day | 2022-04-16 | 2022-04-16 | 1.25
7.1.14 | Sprint Meeting | All | 1 Day | 2022-04-17 | 2022-04-17 | 2.5
7.1.15 | Scrum Meeting | All | 1 Day | 2022-04-18 | 2022-04-18 | 1.25
7.1.16 | Scrum Meeting | All | 1 Day | 2022-04-19 | 2022-04-19 | 1.25
7.1.17 | Scrum Meeting | All | 1 Day | 2022-04-20 | 2022-04-20 | 1.25
7.2 | Machine Learning Development |  |  |  |  | Total: | 33
7.2.1 | Meeting with Jared |  | 1 Day | 2022-03-31 | 2022-03-31 | 5
7.2.2 | Prepare Image Data - Process Results |  | 6 Days | 2022-04-01 | 2022-04-06 | 6
7.2.3 | Scrum Meeting | All | 1 Day | 2022-04-02 | 2022-04-02 | Listed above
7.2.4 | Sprint Meeting | All | 1 Day | 2022-04-03 | 2022-04-03 | Listed above
7.2.5 | Scrum Meeting | All | 1 Day | 2022-04-04 | 2022-04-04 | Listed above
7.2.6 | Scrum Meeting | All | 1 Day | 2022-04-05 | 2022-04-05 | Listed above
7.2.7 | Scrum Meeting | All | 1 Day | 2022-04-06 | 2022-04-06 | Listed above
7.2.8 | Meeting with Jared |  | 1 Day | 2022-04-07 | 2022-04-07 | 5
7.2.9 | Send Prepared Data - Deliver Data |  | 6 Days | 2022-04-08 | 2022-04-13 | 6
7.2.10 | Sprint Meeting | All | 1 Day | 2022-04-10 | 2022-04-10 | Listed above
7.2.11 | Scrum Meeting | All | 1 Day | 2022-04-11 | 2022-04-11 | Listed above
7.2.12 | Scrum Meeting | All | 1 Day | 2022-04-12 | 2022-04-12 | Listed above
7.2.13 | Scrum Meeting | All | 1 Day | 2022-04-13 | 2022-04-13 | Listed above
7.2.14 | Meeting with Jared |  | 1 Day | 2022-04-14 | 2022-04-14 | 5
7.2.15 | Send Prepared Data - Deliver Data |  | 7 Days | 2022-04-14 | 2022-04-20 | 6
7.2.16 | Scrum Meeting | All | 1 Day | 2022-04-16 | 2022-04-16 | Listed above
7.2.17 | Sprint Meeting | All | 1 Day | 2022-04-17 | 2022-04-17 | Listed above
7.2.18 | Scrum Meeting | All | 1 Day | 2022-04-18 | 2022-04-18 | Listed above
7.2.19 | Scrum Meeting | All | 1 Day | 2022-04-19 | 2022-04-19 | Listed above
7.2.20 | Scrum Meeting | All | 1 Day | 2022-04-20 | 2022-04-20 | Listed above
7.3 | Project Management |  |  |  |  | Total: | 3.5
7.3.1 | Gantt Chart Development | Juan | 3 Days | 2022-04-14 | 2022-04-16 | 1.5
7.3.2 | Timesheets | Juan | 3 Days | 2022-04-14 | 2022-04-16 | 0.5
7.3.3 | Costs Estimates | Noah / Juan / Jordan | 3 Days | 2022-04-14 | 2022-04-16 | 1.5
7.4 | Report 4 |  |  |  |  | Total: | 12
7.4.1 | Report 4 (draft) | Noah / Juan / Jordan | 12 Days | 2022-04-14 | 2022-04-25 | 9
7.4.2 | Report 4 (revisions) | Noah / Juan / Jordan | 20 Days | 2022-04-14 | 2022-05-02 | 3
[6 empty] | Total: | 73.5 | (Total for Phase 4)
8 | Phase 5: Final
8.1 | Machine Learning Finalization |  |  |  |  | Total: | 70.75 | (Total for Phase 5)
8.1.1 | ML Algorithim Finalization | All | 15 Days | 2022-04-21 | 2022-05-05 | 20
8.1.2 | Meeting with Jared | All | 1 Day | 2022-04-21 | 2022-04-21 | 6
8.1.3 | Scrum Meeting | All | 1 Day | 2022-04-23 | 2022-04-23 | 1.25
8.1.4 | Sprint Meeting | All | 1 Day | 2022-04-24 | 2022-04-24 | 2.5
8.1.5 | Scrum Meeting | All | 1 Day | 2022-04-25 | 2022-04-25 | 1.25
8.1.6 | Scrum Meeting | All | 1 Day | 2022-04-26 | 2022-04-26 | 1.25
8.1.7 | Scrum Meeting | All | 1 Day | 2022-04-27 | 2022-04-27 | 1.25
8.1.8 | Meeting with Jared | All | 1 Day | 2022-04-28 | 2022-04-28 | 6
8.1.9 | Scrum Meeting | All | 1 Day | 2022-04-30 | 2022-04-30 | 1.25
8.1.10 | Sprint Meeting | All | 1 Day | 2022-05-01 | 2022-05-01 | 2.5
8.1.11 | Scrum Meeting | All | 1 Day | 2022-05-02 | 2022-05-02 | 1.25
8.1.12 | Scrum Meeting | All | 1 Day | 2022-05-03 | 2022-05-03 | 1.25
8.1.13 | Meeting with Jared | All | 1 Day | 2022-05-05 | 2022-05-05 | 2.5
8.2 | Final Report
8.2.1 | Prepare | All | 5 Day | 2022-05-04 | 2022-05-08 | 6.25
8.2.2 | Scrum Meeting | All | 1 Day | 2022-05-04 | 2022-05-04 | 1.25
8.2.3 | Scrum Meeting | All | 1 Day | 2022-05-07 | 2022-05-07 | 1.25
8.2.4 | Sprint Meeting | All | 1 Day | 2022-05-08 | 2022-05-08 | 2.5
8.3 | Prepare for Final Presentation
8.3.1 | Prepare | All | 5 Day | 2022-05-09 | 2022-05-13 | 6.25
8.3.2 | Scrum Meeting | All | 1 Day | 2022-05-09 | 2022-05-09 | 1.25
8.3.3 | Scrum Meeting | All | 1 Day | 2022-05-10 | 2022-05-10 | 1.25
8.3.4 | Scrum Meeting | All | 1 Day | 2022-05-11 | 2022-05-11 | 1.25
8.3.5 | Scrum Meeting | All | 1 Day | 2022-05-13 | 2022-05-13 | 1.25
Formulas:
Start = [Start, row below]
Finish = [Finish, row below]
Finish = [Start]