## Week 2
Time Sheet ¦ Name: Noah Miera |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Team/Scrum Leader |  |  |  |  | Time Sheet ¦ Name: Keith Gross |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Programer
[6 empty] | Week 2 | [14 empty] | Week 2
[5 empty] | 1/30-2022 - 2/5/2022 | [14 empty] | 1/30-2022 - 2/5/2022
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-01-30 |  | 2022-01-31 |  | 2022-02-01 |  | 2022-02-02 |  | 2022-02-03 |  | 2022-02-04 |  | 2022-02-05 |  |  | 2022-01-30 |  | 2022-01-31 |  | 2022-02-01 |  | 2022-02-02 |  | 2022-02-03 |  | 2022-02-04 |  | 2022-02-05
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL |  | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
2.1 | [6 empty] | 1 | 0.5 | [6 empty] | 2.1 | [6 empty] | 1 | 1
3 | [8 empty] | 1.2 | 1.2 |  |  |  |  | 3 | [8 empty] | 1.2 | 1.2
[11 empty] | TOTAL | PLANNED: | 2.2 | [12 empty] | TOTAL | PLANNED: | 2.2
Signature: | [11 empty] | ACTUAL: | 1.7 |  | Signature: | [11 empty] | ACTUAL: | 2.2
Time Sheet ¦ Name: Juan Gonzalez |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Project Manager |  |  |  |  | Time Sheet ¦ Name: Miguel Morales |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Programer
[6 empty] | Week 2 | [14 empty] | Week 2
[5 empty] | 1/30-2022 - 2/5/2022 | [14 empty] | 1/30-2022 - 2/5/2022
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-01-30 |  | 2022-01-31 |  | 2022-02-01 |  | 2022-02-02 |  | 2022-02-03 |  | 2022-02-04 |  | 2022-02-05 |  |  | 2022-01-30 |  | 2022-01-31 |  | 2022-02-01 |  | 2022-02-02 |  | 2022-02-03 |  | 2022-02-04 |  | 2022-02-05
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL |  | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
2.1 | [6 empty] | 1 | 1.5 | [6 empty] | 2.1 | [6 empty] | 1 | 1
3 | [8 empty] | 1.2 | 1.2 |  |  |  |  | 3 | [8 empty] | 1.2 | 1.2
[11 empty] | TOTAL | PLANNED: | 2.2 | [12 empty] | TOTAL | PLANNED: | 2.2
Signature: | [11 empty] | ACTUAL: | 2.7 |  | Signature: | [11 empty] | ACTUAL: | 2.2
Time Sheet ¦ Name: Jordan Fisher |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Documentation/Training
[6 empty] | Week 2 | [11 empty] | 10.5
1/30-2022 - 2/5/2022
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-01-30 |  | 2022-01-31 |  | 2022-02-01 |  | 2022-02-02 |  | 2022-02-03 |  | 2022-02-04 |  | 2022-02-05
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
2.1 | [6 empty] | 1 | 0.5
3 | [8 empty] | 1.2 | 1.2
[11 empty] | TOTAL | PLANNED: | 2.2
Signature: | [11 empty] | ACTUAL: | 1.7

## Week 3
Time Sheet ¦ Name: Noah Miera |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Team/Scrum Leader |  |  |  |  | Time Sheet ¦ Name: Keith Gross |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Programer
[6 empty] | Week 3 | [14 empty] | Week 3
[5 empty] | 2/6-2022 - 2/12/2022 | [14 empty] | 2/6-2022 - 2/12/2022
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-02-06 |  | 2022-02-07 |  | 2022-02-08 |  | 2022-02-09 |  | 2022-02-10 |  | 2022-02-11 |  | 2022-02-12 |  |  | 2022-02-06 |  | 2022-02-07 |  | 2022-02-08 |  | 2022-02-09 |  | 2022-02-10 |  | 2022-02-11 |  | 2022-02-12
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL |  | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
4.1.1 | 0.5 | 1 | [12 empty] | 4.1.1 | 0.5 | 1
4.1.2 |  |  | 0.25 | 0.5 | [10 empty] | 4.1.2 |  |  | 0.25 | 0.25
4.2.1 | [6 empty] | 0.25 | 0.25 | [6 empty] | 4.2.1 | [6 empty] | 0.25 | 0.25
4.2.2 | [8 empty] | 1 | 1 |  |  |  |  | 4.2.2 | [8 empty] | 1 | 1
4.2.3 | [10 empty] | 0.25 | 0.25 |  |  | 4.2.3 | [10 empty] | 0.25 | 0.25
4.4.1-4.3.1-4.3.2-4.3.3 | [12 empty] | 2 | 4 | 4.51 | [12 empty] | 1.5 | 3
[11 empty] | TOTAL | PLANNED: | 4.25 | [12 empty] | TOTAL | PLANNED: | 3.75
Signature: | [11 empty] | ACTUAL: | 7 |  | Signature: | [11 empty] | ACTUAL: | 5.75
Time Sheet ¦ Name: Juan Gonzalez |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Project Manager |  |  |  |  | Time Sheet ¦ Name: Miguel Morales |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Programer
[6 empty] | Week 3 | [14 empty] | Week 3
[5 empty] | 2/6-2022 - 2/12/2022 | [14 empty] | 2/6-2022 - 2/12/2022
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-02-06 |  | 2022-02-07 |  | 2022-02-08 |  | 2022-02-09 |  | 2022-02-10 |  | 2022-02-11 |  | 2022-02-12 |  |  | 2022-02-06 |  | 2022-02-07 |  | 2022-02-08 |  | 2022-02-09 |  | 2022-02-10 |  | 2022-02-11 |  | 2022-02-12
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL |  | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
4.1.1 | 0.5 | 1 | [12 empty] | 4.1.1 | 0.5 | 1
4.1.2 |  |  | 0.25 | 0.5 | [10 empty] | 4.1.2 |  |  | 0.25 | 0.25
4.2.1 | [6 empty] | 0.25 | 0.25 | [6 empty] | 4.2.1 | [6 empty] | 0.25 | 0
4.2.2 | [8 empty] | 1 | 1 |  |  |  |  | 4.2.2 | [8 empty] | 1 | 1
4.2.3 | [10 empty] | 0.25 | 0.25 |  |  | 4.2.3 | [10 empty] | 0.25 | 0.25
4.4.1-4.3.1-4.3.2-4.3.3 | [12 empty] | 2 | 4 | 4.51 | [12 empty] | 1.5 | 1.5
[11 empty] | TOTAL | PLANNED: | 4.25 | [12 empty] | TOTAL | PLANNED: | 3.75
Signature: | [11 empty] | ACTUAL: | 7 |  | Signature: | [11 empty] | ACTUAL: | 4
Time Sheet ¦ Name: Jordan Fisher |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Documentation/Training
Week 3
2/6-2022 - 2/12/2022
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-02-06 |  | 2022-02-07 |  | 2022-02-08 |  | 2022-02-09 |  | 2022-02-10 |  | 2022-02-11 |  | 2022-02-12
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
4.1.1 | 0.5 | 1
4.1.2 |  |  | 0.25 | 0.5
4.2.1 | [6 empty] | 0.25 | 0.25
4.2.2 | [8 empty] | 1 | 1
4.2.3 | [10 empty] | 0.25 | 0.25
4.4.1-4.3.1-4.3.2-4.3.3 | [12 empty] | 2 | 4
[11 empty] | TOTAL | PLANNED: | 4.25
Signature: | [11 empty] | ACTUAL: | 7

## Week 4
Time Sheet ¦ Name: Noah Miera |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Team/Scrum Leader |  |  |  |  | Time Sheet ¦ Name: Keith Gross |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Programer
[6 empty] | Week 4 | [14 empty] | Week 4
[5 empty] | 2022-02-13 | - | 2022-02-19 | [12 empty] | 2022-02-13 | - | 2022-02-19
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-02-13 |  | 2022-02-14 |  | 2022-02-15 |  | 2022-02-16 |  | 2022-02-17 |  | 2022-02-18 |  | 2022-02-19 |  |  | 2022-02-13 |  | 2022-02-14 |  | 2022-02-15 |  | 2022-02-16 |  | 2022-02-17 |  | 2022-02-18 |  | 2022-02-19
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL |  | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
4.5.2 | 0.5 | 0.5 | [12 empty] | 4.5.2 | 0.5 | 0.5
4.5.3 |  |  | 0.25 | 0.25 | [10 empty] | 4.5.3 |  |  | 0.25 | 0.25
4.4.1-4.3.1-4.3.2-4.3.3 | 2 | 8 | [12 empty] | 4.51 | 1.5 | 3
[11 empty] | TOTAL | PLANNED: | 2.75 | [12 empty] | TOTAL | PLANNED: | 2.25
Signature: | [11 empty] | ACTUAL: | 8.75 |  | Signature: | [11 empty] | ACTUAL: | 3.75
Time Sheet ¦ Name: Juan Gonzalez |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Project Manager |  |  |  |  | Time Sheet ¦ Name: Miguel Morales |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Programer
[6 empty] | Week 4 | [14 empty] | Week 4
[5 empty] | 2022-02-13 | - | 2022-02-19 | [12 empty] | 2022-02-13 | - | 2022-02-19
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-02-13 |  | 2022-02-14 |  | 2022-02-15 |  | 2022-02-16 |  | 2022-02-17 |  | 2022-02-18 |  | 2022-02-19 |  |  | 2022-02-13 |  | 2022-02-14 |  | 2022-02-15 |  | 2022-02-16 |  | 2022-02-17 |  | 2022-02-18 |  | 2022-02-19
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL |  | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
4.5.2 | 0.5 | 0.5 | [12 empty] | 4.5.2 | 0.5 | 0.5
4.5.3 |  |  | 0.25 | 0.25 | [10 empty] | 4.5.3 |  |  | 0.25 | 0.25
4.4.1-4.3.1-4.3.2-4.3.3 | 2 | 6.5 | [12 empty] | 4.51 | 1.5 | 2
[11 empty] | TOTAL | PLANNED: | 2.75 | [12 empty] | TOTAL | PLANNED: | 2.25
Signature: | [11 empty] | ACTUAL: | 7.25 |  | Signature: | [11 empty] | ACTUAL: | 2.75
Time Sheet ¦ Name: Jordan Fisher |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Documentation/Training
Week 4
[5 empty] | 2022-02-13 | - | 2022-02-19
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-02-13 |  | 2022-02-14 |  | 2022-02-15 |  | 2022-02-16 |  | 2022-02-17 |  | 2022-02-18 |  | 2022-02-19
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
4.5.2 | 0.5 | 0.5
4.5.3 |  |  | 0.25 | 0.25
4.4.1-4.3.1-4.3.2-4.3.3 | 2 | 8
[11 empty] | TOTAL | PLANNED: | 2.75
Signature: | [11 empty] | ACTUAL: | 8.75
|  | 3 Days | 2022-02-11 | 2022-02-13
|  | 3 Days | 2022-02-11 | 2022-02-13
|  | 3 Days | 2022-02-11 | 2022-02-13
4.4.1 |  | 4 Days | 2022-02-11 | 2022-02-14 |  | 4.3.1 | Gantt Chart Development |  |  | Juan / Noah |  | 0.5 | 2
[6 empty] | 4.3.2 |  | Timesheets |  | Juan / Jordan |  | 0.25 | 1
[6 empty] | 4.3.3 |  | Costs Estimates |  | Noah / Juan / Jordan |  | 0.25 | 1
[6 empty] | 4.4.1 |  | Report 1 (draft) |  | Noah / Juan / Jordan |  | 1 | 4

## Reworked Week 2
| Timesheet for Week Ending: 2/5/2022 | [5 empty] | Timesheet for Week Ending: 2/5/2022
Team Name | Sushi Team |  |  |  |  | Team Name | Sushi Team
Member Name: | Noah Miera | Role: Team/Scrum Leader |  |  |  | Member Name: | Keith Gross | Role: Programer
Signed: | [5 empty] | Signed:
|  | Planned | Actual |  | Task |  |  | Planned | Actual |  | Task
Date | Task | Hours | Hours | Difference | Completed? | Date | Task | Hours | Hours | Difference | Completed?
2022-02-02 | 2.1 (TACO repo, documentation, and code) | 1 | 0.5 | -0.5 | yes | 2022-02-02 | 2.1 (TACO repo, documentation, and code) | 1 | 1 | 0 | yes
2022-02-03 | 3 (1st Team Meeting) | 1.2 | 1.2 | 0 | yes | 2022-02-03 | 3 (1st Team Meeting) | 1.2 | 1.2 | 0 | yes
Totals for Week in hours |  | 2.2 | 1.7 | -0.5 |  | Totals for Week in hours |  | 2.2 | 2.2 | 0
| Timesheet for Week Ending: 2/5/2022 | [5 empty] | Timesheet for Week Ending: 2/5/2022
Team Name | Sushi Team |  |  |  |  | Team Name | Sushi Team
Member Name: | Juan Gonzalez | Role: Project Manager |  |  |  | Member Name: | Miguel Morales | Role: Programer
Signed: | [5 empty] | Signed:
|  | Planned | Actual |  | Task |  |  | Planned | Actual |  | Task
Date | Task | Hours | Hours | Difference | Completed? | Date | Task | Hours | Hours | Difference | Completed?
2022-02-02 | 2.1 (TACO repo, documentation, and code) | 1 | 1.5 | 0.5 | yes | 2022-02-02 | 2.1 (TACO repo, documentation, and code) | 1 |  | -1 | yes
2022-02-03 | 3 (1st Team Meeting) | 1.2 | 1.2 | 0 | yes | 2022-02-03 | 3 (1st Team Meeting) | 1.2 | 1.2 | 0 | yes
Totals for Week in hours |  | 2.2 | 2.7 | 0.5 |  | Totals for Week in hours |  | 2.2 | 1.2 | -1
Timesheet for Week Ending: 2/5/2022
Team Name | Sushi Team
Member Name: | Jordan Fisher | Role: Documentation/Training
Signed:
|  | Planned | Actual |  | Task
Date | Task | Hours | Hours | Difference | Completed?
2022-02-02 | 2.1 (TACO repo, documentation, and code) | 1 | 0.5 | -0.5 | yes
2022-02-03 | 3 (1st Team Meeting) | 1.2 | 1.2 | 0 | yes
Totals for Week in hours |  | 2.2 | 1.7 | -0.5
Change 2.1 to Mask RCNN

## Reworked Week 3
| Timesheet for Week Ending: 2/12/2022 | [5 empty] | Timesheet for Week Ending: 2/12/2022
Team Name | Sushi Team |  |  |  |  | Team Name | Sushi Team
Member Name: | Noah Miera | Role: Team/Scrum Leader |  |  |  | Member Name: | Keith Gross | Role: Programer
Signed: | [5 empty] | Signed:
|  | Planned | Actual |  | Task |  |  | Planned | Actual |  | Task
Date | Task | Hours | Hours | Difference | Completed? | Date | Task | Hours | Hours | Difference | Completed?
2022-02-06 | 4.1.1 (Team Sprint) | 0.5 | 1 | 0.5 | yes | 2022-02-06 | 4.1.1 (Team Sprint) | 0.5 | 1 | 0.5 | yes
2022-02-07 | 4.1.2 (Team Scrum) | 0.25 | 0.5 | 0.25 | yes | 2022-02-07 | 4.1.2 (Team Scrum) | 0.25 | 0.5 | 0.25 | yes
2022-02-09 | 4.2.1 (Team Scrum) | 0.25 | 0.25 | 0 | yes | 2022-02-09 | 4.2.1 (Team Scrum) | 0.25 | 0.25 | 0 | yes
2022-02-10 | 4.2.2 (Meeting with Client) | 1 | 1 | 0 | yes | 2022-02-10 | 4.2.2 (Meeting with Client) | 1 | 1 | 0 | yes
2022-02-11 | 4.2.3 (Team Scrum) | 0.25 | 0.25 | 0 | yes | 2022-02-11 | 4.2.3 (Team Scrum) | 0.25 | 0.25 | 0 | yes
2022-02-12 | 4.4.1 (Report 1 draft) | 8 | 5 | -3 | no | 2022-02-12 | 4.5.1 (Research Mask R-CNN model | 3 | 3 | 0 | no
2022-02-12 | 4.3.1 (Gantt Chart Development) | 1 | 1 | 0 | no |  | & ML Coding Setup - Part 1)
2022-02-12 | 4.3.3 (Costs Estimates) | 1 | 1 |  | no
Totals for Week in hours |  | 12.25 | 10 | -2.25 |  | Totals for Week in hours |  | 5.25 | 6 | 0.75
| Timesheet for Week Ending: 2/12/2022 | [5 empty] | Timesheet for Week Ending: 2/12/2022
Team Name | Sushi Team |  |  |  |  | Team Name | Sushi Team
Member Name: | Juan Gonzalez | Role: Project Manager |  |  |  | Member Name: | Miguel Morales | Role: Programer
Signed: | [5 empty] | Signed:
|  | Planned | Actual |  | Task |  |  | Planned | Actual |  | Task
Date | Task | Hours | Hours | Difference | Completed? | Date | Task | Hours | Hours | Difference | Completed?
2022-02-06 | 4.1.1 (Team Sprint) | 0.5 | 1 | 0.5 | yes | 2022-02-06 | 4.1.1 (Team Sprint) | 0.5 | 1 | 0.5 | yes
2022-02-07 | 4.1.2 (Team Scrum) | 0.25 | 0.5 | 0.25 | yes | 2022-02-07 | 4.1.2 (Team Scrum) | 0.25 | 0.5 | 0.25 | yes
2022-02-09 | 4.2.1 (Team Scrum) | 0.25 | 0.25 | 0 | yes | 2022-02-09 | 4.2.1 (Team Scrum) | 0.25 | 0.25 | 0 | yes
2022-02-10 | 4.2.2 (Meeting with Client) | 1 | 1 | 0 | yes | 2022-02-10 | 4.2.2 (Meeting with Client) | 1 | 1 | 0 | yes
2022-02-11 | 4.2.3 (Team Scrum) | 0.25 | 0.25 | 0 | yes | 2022-02-11 | 4.2.3 (Team Scrum) | 0.25 | 0.25 | 0 | yes
2022-02-12 | 4.4.1 (Report 1 draft) | 8 | 4 | -4 | no | 2022-02-12 | 4.5.1 (Research Mask R-CNN model | 3
2022-02-12 | 4.3.1 (Gantt Chart Development) | 1 | 1 | 0 | no |  | & ML Coding Setup - Part 1)
Totals for Week in hours |  | 11.25 | 8 | -3.25 |  | Totals for Week in hours |  | 5.25 | 3 | 0.75
Timesheet for Week Ending: 2/12/2022
Team Name | Sushi Team
Member Name: | Jordan Fisher | Role: Documentation/Training
Signed:
|  | Planned | Actual |  | Task
Date | Task | Hours | Hours | Difference | Completed?
2022-02-06 | 4.1.1 (Team Sprint) | 0.5 | 1 | 0.5 | yes
2022-02-07 | 4.1.2 (Team Scrum) | 0.25 | 0.5 | 0.25 | yes
2022-02-09 | 4.2.1 (Team Scrum) | 0.25 | 0.25 | 0 | yes
2022-02-10 | 4.2.2 (Meeting with Client) | 1 | 1 | 0 | yes
2022-02-11 | 4.2.3 (Team Scrum) | 0.25 | 0.25 | 0 | yes
2022-02-12 | 4.4.1 (Report 1 draft) | 8 | 4 | -4 | no
2022-02-12 | 4.3.2 (Timesheets) | 1 | 1 | 0 | no
2022-02-12 | 4.3.3 (Costs Estimates) | 1 | 1 | 0 | no
Totals for Week in hours |  | 12.25 | 9 | -3.25

## Reworked week 4
4
|  | Timesheet for Week Ending: 2/19/2022 | [5 empty] | Timesheet for Week Ending: 2/19/2022
| Team Name | Sushi Team |  |  |  |  | Team Name | Sushi Team
| Member Name: | Noah Miera | Role: Team/Scrum Leader |  |  |  | Member Name: | Keith Gross | Role: Programer
| Signed: | [5 empty] | Signed:
|  |  | Planned | Actual |  | Task |  |  | Planned | Actual |  | Task
| Date | Task | Hours | Hours | Difference | Completed? | Date | Task | Hours | Hours | Difference | Completed?
| 2022-02-13 | Task 4.5.2 (Team Sprint) | 0.5 | 0.5 | 0 | yes | 2022-02-13 | Task 4.5.2 (Team Sprint) | 0.5 | 0.5 | 0 | yes
| 2022-02-13 | Task 4.3.1 (Gantt Chart Development) | 1 | 1 | 0 | yes | 2022-02-13 | Task 4.5.1 (Research Mask R-CNN...) | 3 | 3 | 0 | yes
| 2022-02-13 | Task 4.3.3 (Costs Estimates) | 1 | 1 | 0 | yes | 2022-02-14 | Task 4.5.3 (Team Scrum) | 0.25 | 0.25 | 0 | yes
| 2022-02-13 | Task 4.4.1 (Report 1 draft) | 8 | 8 | 0 | yes | 2022-02-15 | Task 4.5.4 (Research Mask R-CNN...) | 1 | 1 | 0 | yes
| 2022-02-14 | Task 4.5.3 (Scrum meeting) | 0.25 | 0.25 | 0 | yes | 2022-02-15 | Task 4.5.5 (Scrum meeting) | 0.25 | 0.25 | 0 | yes
| 2022-02-15 | Task 4.5.4 (Research Mask R-CNN...) | 1 | 1 | 0 | no | 2022-02-16 | Task 4.5.6 (Scrum meeting) | 0.25 | 0.25 | 0 | yes
| 2022-02-15 | Task 4.5.5 (Scrum meeting) | 0.25 | 0.25 | 0 | yes | 2022-02-18 | Task 5.1.1 (Scrum meeting) | 0.25 | 0.25 | 0 | yes
| 2022-02-16 | Task 4.5.6 (Scrum meeting) | 0.25 | 0.25 | 0 | yes
| 2022-02-17 | Task 5.2.1 (Meeting with Jared) | 1 | 1 | 0 | yes
| 2022-02-18 | Task 5.1.1/5.2.4 (Scrum meeting) | 0.25 | 0.25 | 0 | yes
| 2022-02-19 | Task 4.4.2 (Report 1 revisions) | 7 | 7 | 0 | no
| Totals for Week in hours |  | 20.5 | 20.5 | 0 |  | Totals for Week in hours |  | 5.5 | 5.5 | 0
|  | Timesheet for Week Ending: 2/19/2022 | [5 empty] | Timesheet for Week Ending: 2/19/2022
| Team Name | Sushi Team |  |  |  |  | Team Name | Sushi Team
| Member Name: | Juan Gonzalez | Role: Project Manager |  |  |  | Member Name: | Miguel Morales | Role: Programer
| Signed: | [5 empty] | Signed:
|  |  | Planned | Actual |  | Task |  |  | Planned | Actual |  | Task
| Date | Task | Hours | Hours | Difference | Completed? | Date | Task | Hours | Hours | Difference | Completed?
| 2022-02-13 | Task 4.5.2 (Team Sprint) | 0.5 | 0.5 | 0 | yes | 2022-02-13 | Task 4.5.2 (Team Sprint) | 0.5 | 0.5 | 0 | yes
| 2022-02-13 | Task 4.3.1 (Gantt Chart Development) | 1 | 1 | 0 | yes | 2022-02-13 | Task 4.5.1 (Research Mask R-CNN) | 1.5 | 2 | 0.5 | yes
| 2022-02-13 | Task 4.3.3 (Costs Estimates) | 1 | 1 | 0 | yes | 2022-02-14 | Task 4.5.3 (Team Scrum) | 0.25 | 0.25 | 0 | yes
| 2022-02-13 | Task 4.4.1 (Report 1 draft) | 8 | 8 | 0 | yes | 2022-02-15 | Task 4.5.4 (Research Mask R-CNN model) | 1 | 1 | 0 | yes
| 2022-02-14 | Task 4.5.3 (Scrum meeting) | 0.25 | 0.25 | 0 | yes | 2022-02-15 | Task 4.5.5 (Scrum meeting) | 0.25 | 0.25 | 0 | yes
| 2022-02-15 | Task 4.5.4 (Research Mask R-CNN...) | 1 |  | -1 | no | 2022-02-16 | Task 4.5.6 (Scrum meeting) | 0.25 | 0.25 | 0 | yes
| 2022-02-15 | Task 4.5.5 (Scrum meeting) | 0.25 | 0.25 | 0 | yes | 2022-02-18 | Task 5.1.1 (Scrum meeting) | 0.25 | 0.25 | 0 | yes
| 2022-02-16 | Task 4.5.6 (Scrum meeting) | 0.25 | 0.25 | 0 | yes
| 2022-02-17 | Task 5.2.1 (Meeting with Jared) | 1 | 1 | 0 | yes
| 2022-02-18 | Task 5.1.1/5.2.4 (Scrum meeting) | 0.25 | 0.25 | 0 | yes
| 2022-02-19 | Task 4.4.2 (Report 1 revisions) | 7 | 0 | -7 | no
| Totals for Week in hours |  | 20.5 | 12.5 | -8 |  | Totals for Week in hours |  | 4 | 4.5 | 0.5
Timesheet for Week Ending: 2/19/2022
| Team Name | Sushi Team
| Member Name: | Jordan Fisher | Role: Documentation/Training
Signed:
|  |  | Planned | Actual |  | Task
| Date | Task | Hours | Hours | Difference | Completed?
| 2022-02-13 | Task 4.5.2 (Team Sprint) | 0.5 | 0.5 | 0 | yes
| 2022-02-13 | Task 4.3.2 (Timesheets) | 0.25 | 1 | 0.75 | yes
| 2022-02-13 | Task 4.4.1 (Report 1 draft) | 1 | 6 | 5 | yes
| 2022-02-14 | Task 4.5.3 (Team Scrum) | 0.25 | 0.25 | 0 | yes
| 2022-02-15 | Task 4.5.4 (Research Mask R-CNN model) | 1 | 1 | 0 | yes
| 2022-02-15 | Task 4.5.5 (Scrum meeting) | 0.25 | 0.25 | 0 | yes
| 2022-02-16 | Task 4.5.6 (Scrum meeting) | 0.25 | 0.25 | 0 | yes
| 2022-02-18 | Task 5.1.1 (Scrum meeting) | 0.25 | 0.25 | 0 | yes
0
0
| Totals for Week in hours |  | 3.75 | 9.5 | 5.75

## Reworked week 5
| Timesheet for Week Ending: 2/26/2022 | [5 empty] | Timesheet for Week Ending: 2/26/2022
Team Name | Sushi Team |  |  |  |  | Team Name | Sushi Team
Member Name: | Noah Miera | Role: Team/Scrum Leader |  |  |  | Member Name: | Keith Gross | Role: Programer
Signed: | [5 empty] | Signed:
|  | Planned | Actual |  | Task |  |  | Planned | Actual |  | Task
Date | Task | Hours | Hours | Difference | Completed? | Date | Task | Hours | Hours | Difference | Completed?
2022-02-21 | Task 5.2.4 (Scrum Meeting) | 0.25 |  | -0.25 |  | 2022-02-21 | Task 5.2.4 (Scrum Meeting) | 0.25 |  | -0.25
2022-02-22 | Task 5.2.5 (Scrum Meeting) | 0.25 |  | -0.25 |  | 2022-02-22 | Task 5.2.5 (Scrum Meeting) | 0.25 |  | -0.25
2022-02-23 | Task 5.2.6 (Research Image Processing) | 1 |  | -1 |  | 2022-02-23 | Task 5.2.6 (Research Image Processing) | 1 |  | -1
2022-02-23 | Task 5.2.7 (Scrum meeting) | 0.25 |  | -0.25 |  | 2022-02-23 | Task 5.2.7 (Scrum meeting) | 0.25 |  | -0.25
2022-02-24 | Task 5.2.8 (Meeting with Jared) | 1 |  | -1 |  | 2022-02-24 | Task 5.2.8 (Meeting with Jared) | 1 |  | -1
|  |  |  | 0 | [5 empty] | 0
2022-02-25 | Task 5.5.2 (Scrum Meeting) | 0.25 |  | -0.25 |  | 2022-02-25 | Task 5.5.2 (Scrum Meeting) | 0.25 |  | -0.25
2022-02-26 | Task 5.5.3 (Sprint Meeting) | 0.5 |  | -0.5 |  | 2022-02-26 | Task 5.5.3 (Sprint Meeting) | 0.5 |  | -0.5
|  |  |  | 0 | [5 empty] | 0
|  |  |  | 0 | [5 empty] | 0
Totals for Week in hours |  | 3.5 | 0 | 0 |  | Totals for Week in hours |  | 3.5 | 0 | 0
| Timesheet for Week Ending: 2/26/2022 | [5 empty] | Timesheet for Week Ending: 2/26/2022
Team Name | Sushi Team |  |  |  |  | Team Name | Sushi Team
Member Name: | Juan Gonzalez | Role: Project Manager |  |  |  | Member Name: | Miguel Morales | Role: Programer
Signed: | [5 empty] | Signed:
|  | Planned | Actual |  | Task |  |  | Planned | Actual |  | Task
Date | Task | Hours | Hours | Difference | Completed? | Date | Task | Hours | Hours | Difference | Completed?
2022-02-21 | Task 5.2.4 (Scrum Meeting) | 0.25 |  | -0.25 |  | 2022-02-21 | Task 5.2.4 (Scrum Meeting) | 0.25 |  | -0.25
2022-02-22 | Task 5.2.5 (Scrum Meeting) | 0.25 |  | -0.25 |  | 2022-02-22 | Task 5.2.5 (Scrum Meeting) | 0.25 |  | -0.25
2022-02-23 | Task 5.2.6 (Research Image Processing) | 1 |  | -1 |  | 2022-02-23 | Task 5.2.6 (Research Image Processing) | 1 |  | -1
2022-02-23 | Task 5.2.7 (Scrum meeting) | 0.25 |  | -0.25 |  | 2022-02-23 | Task 5.2.7 (Scrum meeting) | 0.25 |  | -0.25
2022-02-24 | Task 5.2.8 (Meeting with Jared) | 1 |  | -1 |  | 2022-02-24 | Task 5.2.8 (Meeting with Jared) | 1 |  | -1
|  |  |  | 0 | [5 empty] | 0
2022-02-25 | Task 5.5.2 (Scrum Meeting) | 0.25 |  | -0.25 |  | 2022-02-25 | Task 5.5.2 (Scrum Meeting) | 0.25 |  | -0.25
2022-02-26 | Task 5.5.3 (Sprint Meeting) | 0.5 |  | -0.5 |  | 2022-02-26 | Task 5.5.3 (Sprint Meeting) | 0.5 |  | -0.5
|  |  |  | 0 | [5 empty] | 0
|  |  |  | 0 | [5 empty] | 0
Totals for Week in hours |  | 3.5 | 0 | 0 |  | Totals for Week in hours |  | 3.5 | 0 | 0
Timesheet for Week Ending: 2/26/2022
Team Name | Sushi Team
Member Name: | Jordan Fisher | Role: Documentation/Training
Signed:
|  | Planned | Actual |  | Task
Date | Task | Hours | Hours | Difference | Completed?
2022-02-21 | Task 5.2.4 (Scrum Meeting) | 0.25 |  | -0.25
2022-02-22 | Task 5.2.5 (Scrum Meeting) | 0.25 |  | -0.25
2022-02-23 | Task 5.2.6 (Research Image Processing) | 1 |  | -1
2022-02-23 | Task 5.2.7 (Scrum meeting) | 0.25 |  | -0.25
2022-02-24 | Task 5.2.8 (Meeting with Jared) | 1 |  | -1
0
2022-02-25 | Task 5.5.2 (Scrum Meeting) | 0.25 |  | -0.25
2022-02-26 | Task 5.5.3 (Sprint Meeting) | 0.5 |  | -0.5
0
0
Totals for Week in hours |  | 3.5 | 0 | 0