## Week 2
Time Sheet ¦ Name: Noah Miera | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Team/Scrum Leader | [7 empty] | Total: | 8 | Week 2
134.5
[9 empty] | Week 2 | [15 empty] | 142.5 | Total
[8 empty] | 1/30-2022 - 2/5/2022 | [16 empty] | 142.5
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-01-30 |  |  | 2022-01-31 |  |  | 2022-02-01 |  |  | 2022-02-02 |  |  | 2022-02-03 |  |  | 2022-02-04 |  |  | 2022-02-05 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
2.1 | TACO repo, documentation, and code | [9 empty] | 1 | 0.5 | -0.5 | [9 empty] | Yes
3.1 | 1st Team Meeting | [12 empty] | 1.2 | 1.2 | 0 | [6 empty] | Yes
[25 empty] | TOTAL |  | Minus 2/2
[25 empty] | Plan | 11 | 6
[25 empty] | Actual | 10.5 | 5.5
[18 empty] | TOTAL: | PLANNED: | 2.2
[19 empty] | ACTUAL: | 1.7
Signature: | [18 empty] | DIFFERENCE: | -0.5
Time Sheet ¦ Name: Jordan Fisher | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Documentation/Training
Week 2
1/30-2022 - 2/5/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-01-30 |  |  | 2022-01-31 |  |  | 2022-02-01 |  |  | 2022-02-02 |  |  | 2022-02-03 |  |  | 2022-02-04 |  |  | 2022-02-05 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
2.1 | TACO repo, documentation, and code | [9 empty] | 1 | 0.5 | 0.5 | [9 empty] | Yes
3.1 | 1st Team Meeting | [12 empty] | 1.2 | 1.2 | 0 | [6 empty] | Yes
[18 empty] | TOTAL: | PLANNED: | 2.2
[19 empty] | ACTUAL: | 1.7
Signature: | [18 empty] | DIFFERENCE: | -0.5
Time Sheet ¦ Name: Juan Gonzalez | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Project Manager
Week 2
1/30-2022 - 2/5/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-01-30 |  |  | 2022-01-31 |  |  | 2022-02-01 |  |  | 2022-02-02 |  |  | 2022-02-03 |  |  | 2022-02-04 |  |  | 2022-02-05 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
2.1 | TACO repo, documentation, and code | [9 empty] | 1 | 1.5 | 0.5 | [9 empty] | Yes
3.1 | 1st Team Meeting | [12 empty] | 1.2 | 1.2 | 0 | [6 empty] | Yes
[18 empty] | TOTAL: | PLANNED: | 2.2
[19 empty] | ACTUAL: | 2.7
Signature: | [18 empty] | DIFFERENCE: | 0.5
Time Sheet ¦ Name: Keith Gross | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Programmer
Week 2
1/30-2022 - 2/5/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-01-30 |  |  | 2022-01-31 |  |  | 2022-02-01 |  |  | 2022-02-02 |  |  | 2022-02-03 |  |  | 2022-02-04 |  |  | 2022-02-05 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
2.1 | TACO repo, documentation, and code | [9 empty] | 1 | 1 | 0 | [9 empty] | Yes
3.1 | 1st Team Meeting | [12 empty] | 1.2 | 1.2 | 0 | [6 empty] | Yes
[18 empty] | TOTAL: | PLANNED: | 2.2
[19 empty] | ACTUAL: | 2.2
Signature: | [18 empty] | DIFFERENCE: | 0
Time Sheet ¦ Name: Miguel Morales | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Programmer
Week 2
1/30-2022 - 2/5/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-01-30 |  |  | 2022-01-31 |  |  | 2022-02-01 |  |  | 2022-02-02 |  |  | 2022-02-03 |  |  | 2022-02-04 |  |  | 2022-02-05 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
2.1 | TACO repo, documentation, and code | [9 empty] | 1 | 1 | 0 | [9 empty] | Yes
3.1 | 1st Team Meeting | [12 empty] | 1.2 | 1.2 | 0 | [6 empty] | Yes
[18 empty] | TOTAL: | PLANNED: | 2.2
[19 empty] | ACTUAL: | 2.2
Signature: | [18 empty] | DIFFERENCE: | 0

## Week 3
Time Sheet ¦ Name: Noah Miera | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Team/Scrum Leader | [7 empty] | Total: | 39 | Week 2
96.75
Week 3
2/6/2022 - 2/12/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-02-06 |  |  | 2022-02-07 |  |  | 2022-02-08 |  |  | 2022-02-09 |  |  | 2022-02-10 |  |  | 2022-02-11 |  |  | 2022-02-12 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
3.2.1 | Team Sprint | 0.5 | 1 | 0.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.2.2 | Team Scrum |  |  | 0 | 0.25 | 0.5 | 0.25 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.3.1 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.3.2 | Meeting with Client |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 |  |  | 0 |  |  | 0 | Yes |  | TOTAL
3.3.3 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 | Yes |  | Plan | 46.25
3.4.1 | Gannt Chart Development |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 | No |  | Actual | 39
3.4.3 | Costs Estimates |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 | No
3.5.1 | Report 1 Draft |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 8 | 5 | -3 | No
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[18 empty] | TOTAL: | PLANNED: | 12.25
[19 empty] | ACTUAL: | 10
Signature: | [18 empty] | DIFFERENCE: | -2.25
Time Sheet ¦ Name: Jordan Fisher | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Documentation/Training
Week 3
2/6/2022 - 2/12/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-02-06 |  |  | 2022-02-07 |  |  | 2022-02-08 |  |  | 2022-02-09 |  |  | 2022-02-10 |  |  | 2022-02-11 |  |  | 2022-02-12 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
3.2.1 | Team Sprint | 0.5 | 1 | 0.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.2.2 | Team Scrum |  |  | 0 | 0.25 | 0.5 | 0.25 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.3.1 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.3.2 | Meeting with Client |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 |  |  | 0 |  |  | 0 | Yes
3.3.3 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 | Yes
3.4.2 | Timesheets |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 | No
3.4.3 | Costs Estimates |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 | No
3.5.1 | Report 1 Draft |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 8 | 4 | -4 | No
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[18 empty] | TOTAL: | PLANNED: | 12.25
[19 empty] | ACTUAL: | 9
Signature: | [18 empty] | DIFFERENCE: | -3.25
Time Sheet ¦ Name: Juan Gonzalez | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Project Manager
Week 3
2/6/2022 - 2/12/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-02-06 |  |  | 2022-02-07 |  |  | 2022-02-08 |  |  | 2022-02-09 |  |  | 2022-02-10 |  |  | 2022-02-11 |  |  | 2022-02-12 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
3.2.1 | Team Sprint | 0.5 | 1 | 0.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.2.2 | Team Scrum |  |  | 0 | 0.25 | 0.5 | 0.25 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.3.1 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.3.2 | Meeting with Client |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 |  |  | 0 |  |  | 0 | Yes
3.3.3 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 | Yes
3.4.1 | Gannt Chart Development |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 | No
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.5.1 | Report 1 Draft |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 8 | 4 | -4 | No
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[18 empty] | TOTAL: | PLANNED: | 11.25
[19 empty] | ACTUAL: | 8
Signature: | [18 empty] | DIFFERENCE: | -3.25
Time Sheet ¦ Name: Keith Gross | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Programmer
Week 3
2/6/2022 - 2/12/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-02-06 |  |  | 2022-02-07 |  |  | 2022-02-08 |  |  | 2022-02-09 |  |  | 2022-02-10 |  |  | 2022-02-11 |  |  | 2022-02-12 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
3.2.1 | Team Sprint | 0.5 | 1 | 0.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.2.2 | Team Scrum |  |  | 0 | 0.25 | 0.5 | 0.25 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.3.1 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.3.2 | Meeting with Client |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 |  |  | 0 |  |  | 0 | Yes
3.3.3 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 | Yes
3.6.1 | Research Mask R-CNN model...Part 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 3 | 3 | 0 | No
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[18 empty] | TOTAL: | PLANNED: | 5.25
[19 empty] | ACTUAL: | 6
Signature: | [18 empty] | DIFFERENCE: | 0.75
Time Sheet ¦ Name: Miguel Morales | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Programmer
Week 3
2/6/2022 - 2/12/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-02-06 |  |  | 2022-02-07 |  |  | 2022-02-08 |  |  | 2022-02-09 |  |  | 2022-02-10 |  |  | 2022-02-11 |  |  | 2022-02-12 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
3.2.1 | Team Sprint | 0.5 | 1 | 0.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.2.2 | Team Scrum |  |  | 0 | 0.25 | 0.5 | 0.25 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.3.1 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.3.2 | Meeting with Client |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 |  |  | 0 |  |  | 0 | Yes
3.3.3 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 | Yes
3.6.1 | Research Mask R-CNN model...Part 1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 3 | 3 | 0 | No
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[18 empty] | TOTAL: | PLANNED: | 5.25
[19 empty] | ACTUAL: | 6
Signature: | [18 empty] | DIFFERENCE: | 0.75

## Week 4
Time Sheet ¦ Name: Noah Miera | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Team/Scrum Leader | [7 empty] | Total: | 72.5 | Week 2
24.25
Week 4
2/13/2022 - 2/19/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-02-13 |  |  | 2022-02-14 |  |  | 2022-02-15 |  |  | 2022-02-16 |  |  | 2022-02-17 |  |  | 2022-02-18 |  |  | 2022-02-19 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
3.4.1 | Gannt Chart Development | 1 | 1 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.4.3 | Costs Estimates | 1 | 1 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.5.1 | Report 1 Draft | 8 | 8 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.5.2 | Report 1 Revisions |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 7 | 7 | 0 | No |  | TOTAL
3.6.2 | Team Sprint | 0.5 | 0.5 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes |  | Plan | 80.5
3.6.3 | Team Scrum |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes |  | Actual | 72.5
3.6.4 | Research Mask R-CNN model...Part 2 |  |  | 0 |  |  | 0 | 1 | 0.5 | -0.5 | 1 | 1 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.5 | Team Scrum |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.6 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.7 | Meeting with Client |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 |  |  | 0 |  |  | 0 | Yes
3.6.8 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 | Yes
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[18 empty] | TOTAL: | PLANNED: | 21.5
[19 empty] | ACTUAL: | 21
Signature: | [18 empty] | DIFFERENCE: | -0.5
Time Sheet ¦ Name: Jordan Fisher | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Documentation/Training
Week 4
2/13/2022 - 2/19/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-02-13 |  |  | 2022-02-14 |  |  | 2022-02-15 |  |  | 2022-02-16 |  |  | 2022-02-17 |  |  | 2022-02-18 |  |  | 2022-02-19 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
4.3.2 | Timesheets | 1 | 1 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.4.3 | Costs Estimates | 1 | 1 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.5.1 | Report 1 Draft | 8 | 8 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.5.2 | Report 1 Revisions |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 7 | 4 | -3 | No
3.6.2 | Team Sprint | 0.5 | 0.5 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.3 | Team Scrum |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.4 | Research Mask R-CNN model...Part 2 |  |  | 0 |  |  | 0 | 1 | 0 | -1 | 1 | 0.5 | -0.5 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.5 | Team Scrum |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.6 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.7 | Meeting with Client |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 |  |  | 0 |  |  | 0 | Yes
3.6.8 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 | Yes
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[18 empty] | TOTAL: | PLANNED: | 21.5
[19 empty] | ACTUAL: | 17
Signature: | [18 empty] | DIFFERENCE: | -4.5
Time Sheet ¦ Name: Juan Gonzalez | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Project Manager
Week 4
2/13/2022 - 2/19/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-02-13 |  |  | 2022-02-14 |  |  | 2022-02-15 |  |  | 2022-02-16 |  |  | 2022-02-17 |  |  | 2022-02-18 |  |  | 2022-02-19 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
3.4.1 | Gannt Chart Development | 1 | 1 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.5.1 | Report 1 Draft | 8 | 8 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.5.2 | Report 1 Revisions |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 7 | 0 | -7 | No
3.6.2 | Team Sprint | 0.5 | 0.5 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.3 | Team Scrum |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.4 | Research Mask R-CNN model...Part 2 |  |  | 0 |  |  | 0 | 1 | 1 | 0 | 1 | 2 | 1 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.5 | Team Scrum |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.6 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.7 | Meeting with Client |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 |  |  | 0 |  |  | 0 | Yes
3.6.8 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 | Yes
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[18 empty] | TOTAL: | PLANNED: | 20.5
[19 empty] | ACTUAL: | 14.5
Signature: | [18 empty] | DIFFERENCE: | -6
Time Sheet ¦ Name: Keith Gross | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Programmer
Week 4
2/13/2022 - 2/19/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-02-13 |  |  | 2022-02-14 |  |  | 2022-02-15 |  |  | 2022-02-16 |  |  | 2022-02-17 |  |  | 2022-02-18 |  |  | 2022-02-19 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
3.6.1 | Research Mask R-CNN model...Part 1 | 3 | 3 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.6.9 | Initial Google Street Image Collecting |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 | Yes
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.6.2 | Team Sprint | 0.5 | 0.5 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.3 | Team Scrum |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.4 | Research Mask R-CNN model...Part 2 |  |  | 0 |  |  | 0 | 1 | 0 | -1 | 1 | 0 | -1 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.5 | Team Scrum |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.6 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.7 | Meeting with Client |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 |  |  | 0 |  |  | 0 | Yes
3.6.8 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 | Yes
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[18 empty] | TOTAL: | PLANNED: | 8.5
[19 empty] | ACTUAL: | 6.5
Signature: | [18 empty] | DIFFERENCE: | -2
Time Sheet ¦ Name: Miguel Morales | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Programmer
Week 4
2/13/2022 - 2/19/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-02-13 |  |  | 2022-02-14 |  |  | 2022-02-15 |  |  | 2022-02-16 |  |  | 2022-02-17 |  |  | 2022-02-18 |  |  | 2022-02-19 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
3.6.1 | Research Mask R-CNN model...Part 1 | 3 | 2 | -1 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.6.9 | Initial Google Street Image Collecting |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 3 | 2 | Yes
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.6.2 | Team Sprint | 0.5 | 0.5 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.3 | Team Scrum |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.4 | Research Mask R-CNN model...Part 2 |  |  | 0 |  |  | 0 | 1 | 4 | 3 | 1 | 2 | 1 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.5 | Team Scrum |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.6 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
3.6.7 | Meeting with Client |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1 | 1 | 0 |  |  | 0 |  |  | 0 | Yes
3.6.8 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 | Yes
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[18 empty] | TOTAL: | PLANNED: | 8.5
[19 empty] | ACTUAL: | 13.5
Signature: | [18 empty] | DIFFERENCE: | 5

## Week 5
Time Sheet ¦ Name: Noah Miera | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Team/Scrum Leader | [7 empty] | Total: | 24.25 | Week 2
Week 5
2/20/2022 - 2/26/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-02-20 |  |  | 2022-02-21 |  |  | 2022-02-22 |  |  | 2022-02-23 |  |  | 2022-02-24 |  |  | 2022-02-25 |  |  | 2022-02-26 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
3.6.11 | Team Scrum |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
4.1.1 / 4.2.1 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
4.2.4 | Meeting with Client |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
4.3.1 | Gantt Chart Development |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | TOTAL
3.5.2 | Report 1 Revisions | 7 | 7 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes |  | Plan | 32.25
5.4.1 | Report 2 (draft) |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | Actual | 24.25
4.1.2 / 4.2.3 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
4.5.3 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
4.5.4 | Team Sprint |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
4.2.2 | Research Image Processing |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[18 empty] | TOTAL: | PLANNED: | 7.25
[19 empty] | ACTUAL: | 7.25
Signature: | [18 empty] | DIFFERENCE: | 0
Time Sheet ¦ Name: Jordan Fisher | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Documentation/Training
Week 5
2/20/2022 - 2/26/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-02-20 |  |  | 2022-02-21 |  |  | 2022-02-22 |  |  | 2022-02-23 |  |  | 2022-02-24 |  |  | 2022-02-25 |  |  | 2022-02-26 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
3.6.11 | Team Scrum |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
4.1.1 / 4.2.1 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
4.2.4 | Meeting with Client |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
4.3.2 | Timesheets |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.5.2 | Report 1 Revisions | 7 | 7 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
5.4.1 | Report 2 (draft) |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.1.4 / 5.2.8 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.5.3 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.5.4 | Team Sprint |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.2.7 | Research Image Processing |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
4.3.3 | Costs Estimates |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[18 empty] | TOTAL: | PLANNED: | 7.25
[19 empty] | ACTUAL: | 7.25
Signature: | [18 empty] | DIFFERENCE: | 0
Time Sheet ¦ Name: Juan Gonzalez | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Project Manager
Week 5
2/20/2022 - 2/26/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-02-20 |  |  | 2022-02-21 |  |  | 2022-02-22 |  |  | 2022-02-23 |  |  | 2022-02-24 |  |  | 2022-02-25 |  |  | 2022-02-26 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
3.6.11 | Team Scrum |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
4.1.1 / 4.2.1 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
4.2.4 | Meeting with Client |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.3.1 | Gantt Chart Development |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
3.5.2 | Report 1 Revisions | 7 | 7 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
5.4.1 | Report 2 (draft) |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.1.4 / 5.2.8 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.5.3 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.5.4 | Team Sprint |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.2.7 | Research Image Processing |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
4.3.3 | Costs Estimates |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[18 empty] | TOTAL: | PLANNED: | 7.25
[19 empty] | ACTUAL: | 7.25
Signature: | [18 empty] | DIFFERENCE: | 0
Time Sheet ¦ Name: Keith Gross | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Programmer
Week 5
2/20/2022 - 2/26/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-02-20 |  |  | 2022-02-21 |  |  | 2022-02-22 |  |  | 2022-02-23 |  |  | 2022-02-24 |  |  | 2022-02-25 |  |  | 2022-02-26 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
3.6.11 | Team Scrum |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
4.1.1 / 4.2.1 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
4.2.4 | Meeting with Client |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.2.2 | Initial Litter Annotation Development | 5 | 1 | -4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.1.4 / 5.2.8 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.5.3 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.5.4 | Team Sprint |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.2.7 | Research Image Processing |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[18 empty] | TOTAL: | PLANNED: | 5.25
[19 empty] | ACTUAL: | 1.25
Signature: | [18 empty] | DIFFERENCE: | -4
Time Sheet ¦ Name: Miguel Morales | [6 empty] | Organization: KAAB Machine learning | [8 empty] | Position: Programmer
Week 5
2/20/2022 - 2/26/2022
Task ID | Task Name |  | SUN |  |  | MON |  |  | TUE |  |  | WED |  |  | THU |  |  | FRI |  |  | SAT |  | Task
|  |  | 2022-02-20 |  |  | 2022-02-21 |  |  | 2022-02-22 |  |  | 2022-02-23 |  |  | 2022-02-24 |  |  | 2022-02-25 |  |  | 2022-02-26 |  | Complete?
|  | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE | PLANNED | ACTUAL | DIFFERENCE
3.6.11 | Team Scrum |  |  | 0 | 0.25 | 0.25 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
4.1.1 / 4.2.1 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
4.2.4 | Meeting with Client |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.2.2 | Initial Litter Annotation Development | 5 | 1 | -4 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | Yes
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.1.4 / 5.2.8 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.5.3 | Team Scrum |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.5.4 | Team Sprint |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
5.2.7 | Research Image Processing |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[18 empty] | TOTAL: | PLANNED: | 5.25
[19 empty] | ACTUAL: | 1.25
Signature: | [18 empty] | DIFFERENCE: | -4

## OLD Week 3
Time Sheet ¦ Name: Noah Miera |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Team/Scrum Leader |  |  |  |  | Time Sheet ¦ Name: Keith Gross |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Programer
[6 empty] | Week 3 | [14 empty] | Week 3
[5 empty] | 2/6-2022 - 2/12/2022 | [14 empty] | 2/6-2022 - 2/12/2022
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-02-06 |  | 2022-02-07 |  | 2022-02-08 |  | 2022-02-09 |  | 2022-02-10 |  | 2022-02-11 |  | 2022-02-12 |  |  | 2022-02-06 |  | 2022-02-07 |  | 2022-02-08 |  | 2022-02-09 |  | 2022-02-10 |  | 2022-02-11 |  | 2022-02-12
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL |  | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
4.1.1 | 0.5 | 1 | [12 empty] | 4.1.1 | 0.5 | 1
4.1.2 |  |  | 0.25 | 0.5 | [10 empty] | 4.1.2 |  |  | 0.25 | 0.25
4.2.1 | [6 empty] | 0.25 | 0.25 | [6 empty] | 4.2.1 | [6 empty] | 0.25 | 0.25
4.2.2 | [8 empty] | 1 | 1 |  |  |  |  | 4.2.2 | [8 empty] | 1 | 1
4.2.3 | [10 empty] | 0.25 | 0.25 |  |  | 4.2.3 | [10 empty] | 0.25 | 0.25
4.4.1-4.3.1-4.3.2-4.3.3 | [12 empty] | 2 | 4 | 4.51 | [12 empty] | 1.5 | 3
[11 empty] | TOTAL | PLANNED: | 4.25 | [12 empty] | TOTAL | PLANNED: | 3.75
Signature: | [11 empty] | ACTUAL: | 7 |  | Signature: | [11 empty] | ACTUAL: | 5.75
Time Sheet ¦ Name: Juan Gonzalez |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Project Manager |  |  |  |  | Time Sheet ¦ Name: Miguel Morales |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Programer
[6 empty] | Week 3 | [14 empty] | Week 3
[5 empty] | 2/6-2022 - 2/12/2022 | [14 empty] | 2/6-2022 - 2/12/2022
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT |  | Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-02-06 |  | 2022-02-07 |  | 2022-02-08 |  | 2022-02-09 |  | 2022-02-10 |  | 2022-02-11 |  | 2022-02-12 |  |  | 2022-02-06 |  | 2022-02-07 |  | 2022-02-08 |  | 2022-02-09 |  | 2022-02-10 |  | 2022-02-11 |  | 2022-02-12
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL |  | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
4.1.1 | 0.5 | 1 | [12 empty] | 4.1.1 | 0.5 | 1
4.1.2 |  |  | 0.25 | 0.5 | [10 empty] | 4.1.2 |  |  | 0.25 | 0.25
4.2.1 | [6 empty] | 0.25 | 0.25 | [6 empty] | 4.2.1 | [6 empty] | 0.25 | 0
4.2.2 | [8 empty] | 1 | 1 |  |  |  |  | 4.2.2 | [8 empty] | 1 | 1
4.2.3 | [10 empty] | 0.25 | 0.25 |  |  | 4.2.3 | [10 empty] | 0.25 | 0.25
4.4.1-4.3.1-4.3.2-4.3.3 | [12 empty] | 2 | 4 | 4.51 | [12 empty] | 1.5 | 1.5
[11 empty] | TOTAL | PLANNED: | 4.25 | [12 empty] | TOTAL | PLANNED: | 3.75
Signature: | [11 empty] | ACTUAL: | 7 |  | Signature: | [11 empty] | ACTUAL: | 4
Time Sheet ¦ Name: Jordan Fisher |  |  |  | Organization: KAAB Machine learning | [5 empty] | Position: Documentation/Training
Week 3
2/6-2022 - 2/12/2022
Task ID | SUN |  | MON |  | TUE |  | WED |  | THU |  | FRI |  | SAT
| 2022-02-06 |  | 2022-02-07 |  | 2022-02-08 |  | 2022-02-09 |  | 2022-02-10 |  | 2022-02-11 |  | 2022-02-12
| PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | ACTUAL | PLANNED | Actual | PLANNED | ACTUAL | PLANNED | ACTUAL
4.1.1 | 0.5 | 1
4.1.2 |  |  | 0.25 | 0.5
4.2.1 | [6 empty] | 0.25 | 0.25
4.2.2 | [8 empty] | 1 | 1
4.2.3 | [10 empty] | 0.25 | 0.25
4.4.1-4.3.1-4.3.2-4.3.3 | [12 empty] | 2 | 4
[11 empty] | TOTAL | PLANNED: | 4.25
Signature: | [11 empty] | ACTUAL: | 7

## OLD Reworked Week 3
| Timesheet for Week Ending: 2/12/2022 | [5 empty] | Timesheet for Week Ending: 2/12/2022
Team Name | Sushi Team |  |  |  |  | Team Name | Sushi Team
Member Name: | Noah Miera | Role: Team/Scrum Leader |  |  |  | Member Name: | Keith Gross | Role: Programer
Signed: | [5 empty] | Signed:
|  | Planned | Actual |  | Task |  |  | Planned | Actual |  | Task
Date | Task | Hours | Hours | Difference | Completed? | Date | Task | Hours | Hours | Difference | Completed?
2022-02-06 | 4.1.1 (Team Sprint) | 0.5 | 1 | 0.5 | yes | 2022-02-06 | 4.1.1 (Team Sprint) | 0.5 | 1 | 0.5 | yes
2022-02-07 | 4.1.2 (Team Scrum) | 0.25 | 0.5 | 0.25 | yes | 2022-02-07 | 4.1.2 (Team Scrum) | 0.25 | 0.5 | 0.25 | yes
2022-02-09 | 4.2.1 (Team Scrum) | 0.25 | 0.25 | 0 | yes | 2022-02-09 | 4.2.1 (Team Scrum) | 0.25 | 0.25 | 0 | yes
2022-02-10 | 4.2.2 (Meeting with Client) | 1 | 1 | 0 | yes | 2022-02-10 | 4.2.2 (Meeting with Client) | 1 | 1 | 0 | yes
2022-02-11 | 4.2.3 (Team Scrum) | 0.25 | 0.25 | 0 | yes | 2022-02-11 | 4.2.3 (Team Scrum) | 0.25 | 0.25 | 0 | yes
2022-02-12 | 4.4.1 (Report 1 draft) | 8 | 5 | -3 | no | 2022-02-12 | 4.5.1 (Research Mask R-CNN model | 3 | 3 | 0 | no
2022-02-12 | 4.3.1 (Gantt Chart Development) | 1 | 1 | 0 | no |  | & ML Coding Setup - Part 1)
2022-02-12 | 4.3.3 (Costs Estimates) | 1 | 1 |  | no
Totals for Week in hours |  | 12.25 | 10 | -2.25 |  | Totals for Week in hours |  | 5.25 | 6 | 0.75
| Timesheet for Week Ending: 2/12/2022 | [5 empty] | Timesheet for Week Ending: 2/12/2022
Team Name | Sushi Team |  |  |  |  | Team Name | Sushi Team
Member Name: | Juan Gonzalez | Role: Project Manager |  |  |  | Member Name: | Miguel Morales | Role: Programer
Signed: | [5 empty] | Signed:
|  | Planned | Actual |  | Task |  |  | Planned | Actual |  | Task
Date | Task | Hours | Hours | Difference | Completed? | Date | Task | Hours | Hours | Difference | Completed?
2022-02-06 | 4.1.1 (Team Sprint) | 0.5 | 1 | 0.5 | yes | 2022-02-06 | 4.1.1 (Team Sprint) | 0.5 | 1 | 0.5 | yes
2022-02-07 | 4.1.2 (Team Scrum) | 0.25 | 0.5 | 0.25 | yes | 2022-02-07 | 4.1.2 (Team Scrum) | 0.25 | 0.5 | 0.25 | yes
2022-02-09 | 4.2.1 (Team Scrum) | 0.25 | 0.5 | 0.25 | yes | 2022-02-09 | 4.2.1 (Team Scrum) | 0.25 | 0.25 | 0 | yes
2022-02-10 | 4.2.2 (Meeting with Client) | 1 | 1 | 0 | yes | 2022-02-10 | 4.2.2 (Meeting with Client) | 1 | 1 | 0 | yes
2022-02-11 | 4.2.3 (Team Scrum) | 0.25 | 0.25 | 0 | yes | 2022-02-11 | 4.2.3 (Team Scrum) | 0.25 | 0.25 | 0 | yes
2022-02-12 | 4.4.1 (Report 1 draft) | 8 | 4 | -4 | no | 2022-02-12 | 4.5.1 (Research Mask R-CNN model | 3
2022-02-12 | 4.3.1 (Gantt Chart Development) | 1 | 1 | 0 | no |  | & ML Coding Setup - Part 1)
Totals for Week in hours |  | 11.25 | 8.25 | -3 |  | Totals for Week in hours |  | 5.25 | 3 | 0.75
Timesheet for Week Ending: 2/12/2022
Team Name | Sushi Team
Member Name: | Jordan Fisher | Role: Documentation/Training
Signed:
|  | Planned | Actual |  | Task
Date | Task | Hours | Hours | Difference | Completed?
2022-02-06 | 4.1.1 (Team Sprint) | 0.5 | 1 | 0.5 | yes
2022-02-07 | 4.1.2 (Team Scrum) | 0.25 | 0.5 | 0.25 | yes
2022-02-09 | 4.2.1 (Team Scrum) | 0.25 | 0.25 | 0 | yes
2022-02-10 | 4.2.2 (Meeting with Client) | 1 | 1 | 0 | yes
2022-02-11 | 4.2.3 (Team Scrum) | 0.25 | 0.25 | 0 | yes
2022-02-12 | 4.4.1 (Report 1 draft) | 8 | 4 | -4 | no
2022-02-12 | 4.3.2 (Timesheets) | 1 | 1 | 0 | no
2022-02-12 | 4.3.3 (Costs Estimates) | 1 | 1 | 0 | no
Totals for Week in hours |  | 12.25 | 9 | -3.25